## Code Review 1
Code Review 1
REVIEW MEETING: Lab of Week 5 - 13/02/2024
The aim of this code review meeting is to check that the project workflow is set-up for the team. You may choose to meet some of the feature requirements during this review point, but it is not as necessary.
Checklist Submission 1 (23% of CW mark)
The following must be in place: | Name | Target Date | Status
GitHub project for coursework set-up. | Nat | 2024-01-30 | Done
Product Backlog created. | Ewa | 2024-02-09 | Done
Project builds to self-contained JAR with Maven. | Nat | 2024-02-11
Dockerfile for project set-up and works. | Nat | 2024-02-11
GitHub Actions for project set-up and build is working using JAR, and Docker on GitHub Actions. | Nat | 2024-02-11
Correct branches for GitFlow workflow created - includes master, develop, and release branches. | Nat | 2024-02-11 | Done
First release created on GitHub. | Nat | 2024-02-11
Code of Conduct defined. | Chris | 2024-02-06 | Done
Issues being used on GitHub. | Ewa | 2024-02-09 | Done | Add to Git Issues that the next step is to plan sprints, estimate work + and plan the first retrospective
Tasks defined as user stories. | Ewa | 2024-02-09 | Done
Full use cases defined. | Steve/Chris | 2024-02-11
Use case diagram created. | Steve/Chris | 2024-02-11
Graded Criteria Submission 1 (7% of CW mark)
The following criteria will be assessed for overall quality:
Metrics from GitHub. Also used to assess individual contribution.
Use cases well defined.
Code quality including comments.
Your submissions are delivered via your GitHub repository. The master branch of your GitHub repository should also be submitted to Moodle at each assessment point along with a spreadsheet in Excel format (csv, xls or xlsx) detailing Individual team members' contributions.
Group E Individual Team Member Contribution
Matriculation Number | Code Review 1 | Code Review 2 | Code Review 3 | Final Deliverable
40646470 |  |  |  |  | Nat
40679395 |  |  |  |  | Ewa
40674826 |  |  |  |  | Chris
40582347 |  |  |  |  | Steve
Total | 100 | 100 | 100 | 100

## Code Review 2
Code Review 2
REVIEW MEETING: Lab of Week 9 - 12/03/2024
The aim of this code review is to check that task management is set-up and that the initial requirements gathering has taken place via user stories and use cases. You should have completed at least 50% of the work for the project at this point based on your own estimates.
Checklist Submission 2 (20% of CW mark)
The following must be in place: | Name | Target Date | Status
Project integrated with Zube.io. | All |  | Done
Kanban/Project Board being used.
Sprint Boards being used.
Graded Criteria Submission 2 (10% of CW mark)
The following criteria will be assessed for overall quality:
Metrics from GitHub. Also used to assess individual contribution.
Code quality including comments.
Correct usage of branches.
Continuous integration working.
Suitable unit tests defined.
Tests running on GitHub Actions.
Project requirements met.
Your submissions are delivered via your GitHub repository. The master branch of your GitHub repository should also be submitted to Moodle at each assessment point along with a spreadsheet in Excel format (csv, xls or xlsx) detailing Individual team members' contributions.

## Code Review 3
Code Review 3
REVIEW MEETING: Lab of of Week 12 - 16/04/2024
The aim of this code review is to check that testing has been correctly specified and that the project is deploying correctly. At this stage, all of the work of the project should be completed.
Checklist Submission 3 (22% of CW mark)
The following must be in place: | Name | Target Date | Status
Suitable integration tests defined.
Tests running on GitHub Actions.
Deployment working.
Bug reporting system set-up.
Graded Criteria Submission 3 (8% of CW mark)
The following criteria will be assessed for overall quality:
Metrics from GitHub. Also used to assess individual contribution.
Code quality including comments.
Correct usage of branches.
Continuous integration working.
Kanban/Project Board being used.
Quality and coverage of unit tests.
Project requirements met.
Your submissions are delivered via your GitHub repository. The master branch of your GitHub repository should also be submitted to Moodle at each assessment point along with a spreadsheet in Excel format (csv, xls or xlsx) detailing Individual team members' contributions.

## Final Submission
SUBMISSION DEADLINE: Monday at 15:00 of Week 13 (10% of CW mark) - 22/04/2024?
The final deliverable will be compared automatically to your GitHub repository. The final submission will be assessed based on the following criteria:
Metrics from GitHub. Also used to assess individual contribution.
Code quality including comments.
Correct usage of branches.
Continuous integration working.
Kanban/Project Board being used.
Quality and coverage of unit tests.
Project requirements met.
Your submissions are delivered via your GitHub repository. The master branch of your GitHub repository should also be submitted to Moodle at each assessment point along with a spreadsheet in Excel format (csv, xls or xlsx) detailing Individual team members' contributions.